## Sheet1
Todos | Start | Duration | End | March | March | March | April | April | April | May | May | May
Design the frame | 2017-03-20 | 8 | 2017-03-27
Develop iOS Application | 2017-03-28 | 14 | 2017-04-07
Wire electronics | 2017-03-28 | 7 | 2017-04-04
Develop Wireless controlling | 2017-04-05 | 10 | 2017-04-15
Test wireless control | 2017-04-15 | 5 | 2017-04-19
Develop PID | 2017-04-19 | 10 | 2017-04-29
Test leveling and movement | 2017-04-28 | 5 | 2017-04-28
Begin to reflect upon the project and schedule. | 2017-04-30 | 2 | 2017-05-04
Implement GPS hardware | 2017-05-01 | 5 | 2017-05-05
Develop software for GPS | 2017-05-06 | 14 | 2017-05-18
Test final product | 2017-05-19 | 7 | 2017-05-25
Project writeup | 2017-05-01 | 25 | 2017-05-20

## Sheet3
Item | Cost | Quantity | Total | Link
Brushless Motor + ESC + Prop | 38.33 | 0 | 0 | http://www.ebay.com/itm/4X-A2212-1000KV-Brushless-Motor-w-30A-ESC-1045-Propeller-for-DJI-F450-F550-J0X7-/131913745375?hash=item1eb6ac03df:g:sWIAAOSw0UdXtsqe
LiPo Battery | 13.99 | 1 | 13.99 | https://www.amazon.com/Gens-ace-Battery-2200mAh-Airplane/dp/B00WJN4LG0/ref=sr_1_3?ie=UTF8&qid=1488499661&sr=8-3&keywords=lipo+battery+11.1v
Bluetooth Module | 8.99 | 1 | 8.99 | https://www.amazon.com/Pass-Through-Communication-Compatible-Atomic-Market/dp/B00TNOO438/ref=sr_1_3?ie=UTF8&qid=1488892564&sr=8-3&keywords=bluetooth+arduino
GPS | 17.66 | 1 | 17.66 | https://www.amazon.com/DIYmall-AeroQuad-Antenna-Arduino-Aircraft/dp/B01H5FNA4K/ref=sr_1_2?ie=UTF8&qid=1488500436&sr=8-2&keywords=gps+arduino
MPU 6050 | 6.94 | 0 | 0 | https://www.amazon.com/Kootek-MPU-6050-MPU6050-sensors-Accelerometer/dp/B008BOPN40/ref=sr_1_4?ie=UTF8&qid=1488655663&sr=8-4&keywords=mpu+6050
Wood Screw 34mm, 19mm, 12mm * 3mm 6g A2 Stainless Steel | 7.5 | 0 | 0 | http://www.ebay.com/itm/3mm-6g-A2-STAINLESS-STEEL-WOOD-SCREWS-POZI-CSK-10mm-THROUGH-TO-50mm-/190718538596?var=&hash=item2c67b5f364:m:mWmH-3MwpEqMHxtEfEkZxsw
40.64
Other Options
Brushless motor kit | 58 | 1 | 58 | https://www.amazon.com/RioRand-A2212-1000KV-Outrunner-Quad-Rotor/dp/B00M3UONLM/ref=sr_1_2?ie=UTF8&qid=1488501097&sr=8-2&keywords=4X+A2212+1000KV+Brushless+Motor
GPS | 17.66 | 1 | 17.66 | https://www.amazon.com/DIYmall-AeroQuad-Antenna-Arduino-Aircraft/dp/B01H5FNA4K/ref=sr_1_2?ie=UTF8&qid=1488500436&sr=8-2&keywords=gps+arduino
Multicopter Frame | 12.95 | 1 | 12.95 | http://www.ebay.com/itm/F450-Quadcopter-Multirotor-Kit-Frame-Heighten-Broaden-Landing-Gear-Skids-US-L4U2-/192054167508?hash=item2cb75207d4:g:QisAAOSwJ7RYUmfW8&keywords=quadcopter+frame
Folding props | 16.28 | 1 | 16.28 | http://www.ebay.com/itm/4x-DJI-Mavic-Pro-Quadcopter-Drone-8330-Quick-Release-Folding-Propellers-Black-/122276747402?hash=item1c7843188a:g:kl4AAOSwZQRYWIr5
SD Card writer | 5.9 | 1 | 5.9 | https://www.amazon.com/Storage-Shield-Module-Interface-Arduino/dp/B00SL0QWDU/ref=sr_1_2?ie=UTF8&qid=1488682723&sr=8-2&keywords=Arduino+sd+card
Radio Transmitter & Reciever | 26 | 1 | 26 | http://www.ebay.com/itm/New-Flysky-2-4G-FS-T4B-4-CH-Channel-Radio-Control-RC-Transmitter-Receiver-X9M8-/291899124014?hash=item43f68b292e:g:7hYAAOSw8gVX8ywU