## Sheet1
Todos | Start | Duration | March | March | March | April | April | April | May | May | May | End
Design the frame | 42804 | 23 | [9 empty] | 2017-04-01
Print frame | 2017-04-02 | 3 | [9 empty] | 2017-04-04
Assemble frame | 2017-04-05 | 3 | [9 empty] | 2017-04-07
Electronics | 2017-04-08 | 5 | [9 empty] | 2017-04-12
Develop PID | 2017-04-10 | 10 | [9 empty] | 2017-04-19
Test leveling and movement | 2017-04-20 | 3 | [9 empty] | 2017-04-22
Finish Bluetooth | 2017-04-23 | 5 | [9 empty] | 2017-04-27
Test leveling and movement | 2017-04-28 | 3 | [9 empty] | 2017-04-30
Final testing for bluetooth, self-balancing | 2017-05-01 | 7 | [9 empty] | 2017-05-06
Begin to reflect upon the project and schedule. | 2017-05-07 | 3 | [9 empty] | 2017-05-08
If time allows, do person tracking | 2017-05-09 | 14 | [9 empty] | 2017-05-22
Project writeup | 2017-05-09 | 20 | [9 empty] | 2017-05-31

## Sheet3
Item | Cost | Quantity | Total | Link
Brushless Motor + ESC + Prop | 38.33 | 1 | 38.33 | http://www.ebay.com/itm/4X-A2212-1000KV-Brushless-Motor-w-30A-ESC-1045-Propeller-for-DJI-F450-F550-J0X7-/131913745375?hash=item1eb6ac03df:g:sWIAAOSw0UdXtsqe
LiPo Battery | 13.99 | 1 | 13.99 | https://www.amazon.com/Gens-ace-Battery-2200mAh-Airplane/dp/B00WJN4LG0/ref=sr_1_3?ie=UTF8&qid=1488499661&sr=8-3&keywords=lipo+battery+11.1v
Bluefruit LE | 19.95 | 1 | 19.95 | https://www.adafruit.com/products/1697
MPU 6050 | 4.6 | 0 | 0
BMP 180 | 9.95 | 0 | 0 | https://www.amazon.com/Adafruit-Barometric-Pressure-Temperature-Altitude/dp/B00JHJB2V6/ref=sr_1_1?ie=UTF8&qid=1488504751&sr=8-1&keywords=barometer+arduino
72.27
Other Options
Brushless motor kit | 58 | 1 | 58 | https://www.amazon.com/RioRand-A2212-1000KV-Outrunner-Quad-Rotor/dp/B00M3UONLM/ref=sr_1_2?ie=UTF8&qid=1488501097&sr=8-2&keywords=4X+A2212+1000KV+Brushless+Motor
GPS | 17.66 | 1 | 17.66 | https://www.amazon.com/DIYmall-AeroQuad-Antenna-Arduino-Aircraft/dp/B01H5FNA4K/ref=sr_1_2?ie=UTF8&qid=1488500436&sr=8-2&keywords=gps+arduino
Multicopter Frame | 12.95 | 1 | 12.95 | http://www.ebay.com/itm/F450-Quadcopter-Multirotor-Kit-Frame-Heighten-Broaden-Landing-Gear-Skids-US-L4U2-/192054167508?hash=item2cb75207d4:g:QisAAOSwJ7RYUmfW8&keywords=quadcopter+frame